## Project
Project_ID
Project_1
Project_2
Project_3
Project_4
Project_5
Project_6
Project_7
Project_8
Project_9
Project_10
Project_11
Project_12
Project_13
Project_14
Project_15
Project_16
Project_17
Project_18
Project_19
Project_20
Project_21
Project_22
Project_23
Project_24
Project_25
Project_26
Project_27
Project_28
Project_29
Project_30

## Utilized Budget
Sum Of Money spent | Sum Of Actual_Budget
10392539.89 | 14006647

## Project Duration
Sum Of Project Timeline Days
48545

## Project Work Status
Projects | Project Status
15 | In Progress
12 | Completed
3 | Not Started

## Projects by Stage
Projects | Stages of Construction Project
1 | Plan
2 | Design
3 | Pre- Construction
4 | Procurement
8 | Construction
12 | Post Construction

## Project Completion Percentage
Completion Percentage
76.6333

## Utilized Duration
Utilized Duration | Project Duration
37438.05 | 48545

## Budget Variance
Actual Budget | Planned Budget | Project
222448 | 200203 | Project_4
233925 | 210532 | Project_9
239100 | 215190 | Project_10
584173 | 223967 | Project_13
262993 | 236693 | Project_7
283002 | 254701 | Project_12
313195 | 269825 | Project_25
349260 | 314334 | Project_11
351753 | 333494 | Project_21
628649 | 385939 | Project_26
456745 | 411070 | Project_1
469759 | 422783 | Project_2
598139 | 426183 | Project_3
445952 | 435939 | Project_23
496351 | 446715 | Project_5
410317 | 481846 | Project_24
485336 | 481849 | Project_15
544326 | 489893 | Project_8
455922 | 517539 | Project_20
578994 | 521094 | Project_6
407615 | 537069 | Project_19
578921 | 540377 | Project_22
563897 | 551527 | Project_29
598139 | 551658 | Project_27
508218 | 555032 | Project_17
598139 | 557684 | Project_14
520247 | 576063 | Project_16
584798 | 580209 | Project_18
598139 | 605928 | Project_30
638195 | 628347 | Project_28

## Actual vs Planned Resources by
Actual Resources | Planned Resources | Project
261 | 161 | Project_1
199 | 204 | Project_10
250 | 230 | Project_11
245 | 226 | Project_12
223 | 272 | Project_13
256 | 212 | Project_14
336 | 284 | Project_15
297 | 256 | Project_16
238 | 213 | Project_17
278 | 268 | Project_18
303 | 290 | Project_19
190 | 186 | Project_2
291 | 152 | Project_20
274 | 285 | Project_21
286 | 276 | Project_22
292 | 213 | Project_23
306 | 292 | Project_24
320 | 273 | Project_25
265 | 259 | Project_26
150 | 259 | Project_27
308 | 265 | Project_28
284 | 233 | Project_29
150 | 162 | Project_3
150 | 237 | Project_30
239 | 215 | Project_4
230 | 274 | Project_5
268 | 211 | Project_6
251 | 261 | Project_7
197 | 174 | Project_8
285 | 279 | Project_9

## Workload
Completed | Remaining | Overdue | Project
201 | 0 | 60 | Project_1
153 | 0 | 46 | Project_10
163 | 63 | 25 | Project_11
189 | 0 | 56 | Project_12
172 | 0 | 51 | Project_13
166 | 64 | 26 | Project_14
218 | 84 | 34 | Project_15
229 | 0 | 68 | Project_16
155 | 60 | 24 | Project_17
214 | 0 | 64 | Project_18
233 | 0 | 70 | Project_19
124 | 48 | 19 | Project_2
189 | 73 | 29 | Project_20
211 | 0 | 63 | Project_21
220 | 0 | 66 | Project_22
190 | 73 | 29 | Project_23
199 | 77 | 31 | Project_24
208 | 80 | 32 | Project_25
172 | 66 | 27 | Project_26
0 | 259 | 0 | Project_27
200 | 77 | 31 | Project_28
185 | 71 | 28 | Project_29
0 | 162 | 0 | Project_3
0 | 237 | 0 | Project_30
184 | 0 | 55 | Project_4
150 | 58 | 23 | Project_5
174 | 67 | 27 | Project_6
193 | 0 | 58 | Project_7
128 | 49 | 20 | Project_8
185 | 71 | 29 | Project_9