## Donstroy-II Brief Report 15-04
Donstroy II - Planned & Realized Unit Man-Hours and Tasks Efficiency Situation
ATT :
[22 empty] | Current Date : |  |  | 2008-04-16 |  |  |  | C1 | Below "0" Level Civil Works | Quantity | Unit | Planned Unit Man-Hour | Realized Unit Man-Hour | Efficiency (%)
[22 empty] | Report Includes : |  |  | Cover Page |  |  |  | C11 | Sub-foundation Civil Works
[22 empty] | Report Date : |  |  | 2008-04-15 |  |  |  |  | Concrete breaking & cleaning around existing steel colums | 66 | pcs | 15 | 62.0833 | 24.16%
[30 empty] | Natural soil compaction & Site Preparation Works & Removal of Muddy Soil | 10510.41 | m² | 0.2 | 0.37327 | 53.58%
[30 empty] | Earthing (Grounding) at Sub-Foundation level | 10510.41 | m² | 0.1 | 0.054081 | 184.9%
| PROJECT INFORMATION | [8 empty] | 2008-04-15 |  |  |  |  | Max / Min |  |  | Wind | Humidity | [10 empty] | Channel opening and laying of gravel for drainage at foundation level | 400 | m³ | 1.2 | 0.98631 | 121.7%
| PROJECT NAME |  | Donstroy-II Multiuse Office and Shopping Complex at 41, Oruzheyny Lane, Moscow | [6 empty] | Sunrise 06:25 (MSK) | [8 empty] | 95% | [10 empty] | Geo-textile laying (1 layer - 250 gr/m²) | 10653.6 | m² | 0.15 | 0.084152 | 178.2%
| SCOPE OF WORK |  | Donstroy-II Civil, Architectural, Facade, Electrical, Mechanicalt Works in accordance with "Shell and Core" contract regulations. | [6 empty] | Sunset 20:33 (MSK) | [19 empty] | Granite gravel filling (h= 15 cm) | 10510.41 | m² | 0.18 | 0.25098 | 71.72%
[30 empty] | Polyethylene sheet laying (1 layer - 100 mic.) | 10510.41 | m² | 0.12 | 0.060627 | 197.9%
| CONTRACT NO and AWARD DATE |  | No. 2/OR-GP-07 / 10.08.2007 | [26 empty] | Lean concrete wire mesh installation (100 mm x 100 mm - 5 mm)(horizontal) | 10510.41 | m² | 0.3 | 0.21729 | 138.1%
| Actual Start Date |  | 2007-11-01 |  | Construction Finish Date |  | 2009-12-18 | [22 empty] | Lean concrete Pouring (B15 - h= 10 cm)(horizontal) | 1051.041 | m³ | 1.75 | 3.1185 | 56.12%
[30 empty] | Lean concrete wire mesh installation (100 mm x 100 mm - 5 mm)(vertical) | 652 | m² | 0.35 | 0.56232 | 62.24%
| PROJECT OVERALL PROGRESS | [28 empty] | Vertical lean concrete formwork | 652 | m² | 1.8 | 3.1718 | 56.75%
[30 empty] | Lean concrete Pouring (B15 - t=15 cm)(vertical) | 140 | m³ | 1.5 | 4.1169 | 36.44% |  | 2007-11-01 | 2007-12-01 | 2008-01-01 | 2008-02-01 | 2008-03-01 | 2008-04-01 | 2008-05-01 | 2008-06-01 | 2008-07-01 | 2008-08-01 | 2008-09-01 | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01
| DS-II CUMULATIVE PROGRESS | [28 empty] | Horizontal water insulation (2 layers - Tehnoelast EPP w/ primer - 4mm) | 10510.41 | m² | 1.5 | 0.26669 | 562.5% | Planned Monthly Cumulative S-Curve | 0.1634% | 0.8565% | 2.158% | 4.589% | 8.078% | 10.99% | 13.42% | 16.1% | 19.59% | 23.21% | 28.3% | 34.2% | 39.93% | 45.7% | 51.28% | 55.28% | 60.45% | 66.32% | 72.59% | 78.1% | 83.35% | 88.1% | 92.63% | 96.34% | 98.69% | 99.82% | 100%
| Planned | Actual | Variance | [26 empty] | Vertical water insulation (2 layers - Tehnoelast EPP w/ primer - 4mm) | 628.544 | m² | 2 | 0.86446 | 231.4% | Realized Monthly Cumulative S-Curve | 2007-11-01: 0.1657%; 2007-12-01: 0.851%; 2008-01-01: 2.126%; 2008-02-01: 4.417%; 2008-03-01: 7.92%
| 9.709% | 8.683% | -1.025% | [26 empty] | Water insulation around existing steel columns | 66 | pcs | 25 | 6.1 | 409.8%
[30 empty] | Protective screed above water insulation (h= 5 cm) | 525.5205 | m³ | 1.5 | 5.0316 | 29.81%
[29 empty] | C12 | Foundation R/C Works
| DS-II DAILY PROGRESS | [28 empty] | Formwork | 1696.064 | m² | 1.8 | 2.779 | 64.77%
| Planned | Actual | Variance | [26 empty] | Reinforcement | 4300 | ton | 35 | 36.5863 | 95.66%
| 0.09169% | 0.028% | -0.06369% | [26 empty] | Reinforced Concrete | 17162.548 | m³ | 1.4 | 0.66322 | 211.1%
WORK COMPLETE (% COMPLETE) as of 15/04/2008
|  |  |  | Mob. & Demob. & Health & Safety inc. Site Cleaning & Snow Removal |  |  | Civil Works |  |  |  | Architectural Works |  |  |  | Facade & Roofing Works |  |  | External Works |  |  | Mechanical Works |  |  | Electical Works
| TITLE |  |  | Planned | Executed | Variance | Planned | Executed | Variance |  | Planned |  | Executed | Variance | Planned | Executed | Variance | Planned | Executed | Variance | Planned | Executed | Variance | Planned | Executed | Variance
| Mobilization |  |  | 86.36% | 86.36% | 0%
| Demobilization |  |  | 0% | 0% | 0%
| Health & Safety inc. Site Cleaning & Snow Removal |  |  | 19.5% | 19.5% | 0%
| Sub-Foundation Civil Works | [5 empty] | 100% | 100% | 0%
| Foundation Civil Works | [5 empty] | 100% | 100% | 0%
| Substructure (-6;-1) Civil Works | [5 empty] | 25.45% | 10.6% | -14.86%
| Superstructure (+1;+34) Civil Works | [5 empty] | 0% | 0% | 0%
| Flooring Works | [9 empty] | 0% |  | 0% | 0%
| Ceiling Works | [9 empty] | 0% |  | 0% | 0%
| Walls & Partitions Works | [9 empty] | 0% |  | 0% | 0%
| Doors & Gates | [9 empty] | 0% |  | 0% | 0%
| Installation of Light Enclosures | [9 empty] | 0% |  | 0% | 0%
| Facade Cladding | [13 empty] | 0% | 0% | 0%
| Roofing Works | [13 empty] | 0% | 0% | 0%
| External Works | [16 empty] | 0% | 0% | 0% | [10 empty] | Cumulative Progress
| Mechanical Works | [19 empty] | 0% | 0% | 0% | [6 empty] | Mob. & Demob. & Health & Safety | Planned | 60.73%
| Electrical Works | [22 empty] | 0% | 0% | 0% |  |  |  |  | Realized | 60.73%
| BUILDING WORK PROGRESS |  |  | 60.73% | 60.73% | 0% | 19.72% | 17.07% | -2.641% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Civil Works | Planned | 19.72%
[31 empty] | Realized | 17.07%
[30 empty] | Architectural Works | Planned | 0%
[31 empty] | Realized | 0%
c" | [29 empty] | Facade & Roofing Works | Planned | 0%
[31 empty] | Realized | 0%
[30 empty] | External Works | Planned | 0%
[31 empty] | Realized | 0%
[30 empty] | Mechanical Works | Planned | 0%
[31 empty] | Realized | 0%
[30 empty] | Electrical Works | Planned | 0%
[31 empty] | Realized | 0%
| PERSONNEL REPORT | [10 empty] | MAN-HOURS REALIZATION REPORT | [8 empty] | MACHINERY & EQUIPMENTS LIST as of 15-04-2008.
| 2008-04-15 |  |  | Turkish |  | Local |  | Total | [8 empty] | Cumulative |  | Daily |  |  |  |  | Unit | Total | On-Operation | Broken-Down
| ENKA | [10 empty] | Type of Task |  |  |  |  | Planned | Realized as of 15-04-08 | Daily Man-Hours on 15-04-08 | Realization Pct. (%) | Isimak Master (Space Heater) |  |  | pcs | 22 | 22
| Management |  |  | 3 | 100% |  | 0% | 3 | 100% |  |  | Mobilization & Demobilization |  |  |  |  | 98000 | 72593 | 227 | 74.07% | BobCAT S175 |  |  | pcs | 2 | 2
| Office Staff |  |  | 15 | 51.72% | 14 | 48.28% | 29 | 100% |  |  | HSE |  |  |  |  | 40000 | 30823 | 613 | 77.06% | Putzmeister 1409 Stationary Concrete Pump |  |  | pcs | 1 | 1
| Field Supervision |  |  | 16 | 69.57% | 7 | 30.43% | 23 | 100% |  |  | Civil Works |  |  |  |  | 1508103.3153 | 253772 | 3283 | 16.83% | Putzmeister 2110 Stationary Concrete Pump |  |  | pcs | 1 | 1
| Direct Labor |  |  | 103 | 28.77% | 255 | 71.23% | 358 | 100% |  |  | Architectural Works |  |  |  |  | 1052713.415 |  |  | 0% | Wacker Compactor RD7H |  |  | pcs
| Indirect Labor (Security, Warehouse, Time Keeper, Machinery Operator etc.) |  |  | 29 | 29.29% | 70 | 70.71% | 99 | 100% |  |  | Facade Cladding & Roofing Works |  |  |  |  | 229930.75 |  |  | 0% | Compressor Atlas Copco |  |  | pcs | 3 | 3
| First Aid (Doctor, Nurse) |  |  |  | 0% | 3 | 100% | 3 | 100% |  |  | External Works |  |  |  |  | 950 |  |  | 0% | Mobile Crane (30 ton - TADANO) |  |  | pcs | 1 | 1
| General Total |  |  | 166 | 32.23% | 349 | 67.77% | 515 | 100% |  |  | Mechanical Works |  |  |  |  | 497750.8077 |  |  | 0% | Rebar Twisting Equipment MB 42 |  |  | pcs | 4 | 3 | 1
[12 empty] | Electrical Works |  |  |  |  | 503145.2583 |  |  | 0% | Rebar Cutting Equipment MHK 42 |  |  | pcs | 4 | 4
[12 empty] | GRAND TOTAL |  |  |  |  | 3930593.5463 | 357188 | 4123 | 9.087% | Manitaou Forklift |  |  | pcs | 1 | 1 |  | 315549
[21 empty] | Tower Crane |  |  | pcs | 2 | 2 |  | 41639
[21 empty] | Mobile Pump Putzmeister M38Z |  |  | pcs | 1 |  | 1
[21 empty] | Dipaz Air Heater 300 |  |  | pcs | 2 | 2
[21 empty] | Note: The Installation of Third Tower Crane continues as of April,15. | [8 empty] | Project Materials Delivered to the Construction Site on February,14 , 2008
| REMARKS | [14 empty] | Mümtaz Okan İLCİ
[30 empty] | MATERIAL DESCRIPTION | QUANTITY | UNIT | Supplier
[30 empty] | Granite Gravel (20x40) | 152 | m³ | EGIDA
[30 empty] | Rebar Q32 | 75.075 | ton | EVROMETAL-STOLISA
Revision
| 01 |  |  | M.C.CELEBIOGLU |  | O.İLCİ
| No | Date : |  | Prepared by : |  | Checked by : |  |  | Description
7.1429
Cumulative Man-Hour
[21 empty] | Mobile Crane (25 ton - MAZ) |  |  |  | pcs | 1
[28 empty] | Timber 50x100x6000 | 8 | m³ | Stroyservis
[28 empty] | Timber 100x100x6000 | 2 | m³ | Stroyservis
[29 empty] | Concrete Milk (Malako) | 6 | m³ | ATP BETON
+7C
+3C
12
43
16
8
9
8
43
12
15
16
8
11
10
11
4
9
6
Note on I14: Mcelebioglu: 18/01/2008 Saha Teslimi +23 AY (Construction Finish)

## Task Efficiency
Donstroy II - Planned & Realized Unit Man-Hours and Tasks Efficiency Situation
C1 | Below "0" Level Civil Works |  | Unit | Planned Unit Man-Hour | Realized Unit Man-Hour | Efficiency (%)
C11 | Sub-foundation Civil Works
| Concrete breaking & cleaning around existing steel colums |  | pcs | 15 | 62.0833 | 24.16% | Concrete breaking & cleaning around existing steel colums | 24.16%
| Natural soil compaction & Site Preparation Works & Removal of Muddy Soil |  | m² | 0.2 | 0.37114 | 53.89% | Natural soil compaction & Site Preparation Works & Removal of Muddy Soil | 53.89%
| Earthing (Grounding) at Sub-Foundation level |  | m² | 0.1 | 0.053773 | 186% | Earthing (Grounding) at Sub-Foundation level | 186%
| Channel opening and laying of gravel for drainage at foundation level |  | m³ | 1.2 | 0.98631 | 121.7% | Channel opening and laying of gravel for drainage at foundation level | 121.7%
| Geo-textile laying (1 layer - 250 gr/m²) |  | m² | 0.15 | 0.083673 | 179.3% | Geo-textile laying (1 layer - 250 gr/m²) | 179.3%
| Granite gravel filling (h= 15 cm) |  | m² | 0.18 | 0.24955 | 72.13% | Granite gravel filling (h= 15 cm) | 72.13%
| Polyethylene sheet laying (1 layer - 100 mic.) |  | m² | 0.12 | 0.057047 | 210.4% | Polyethylene sheet laying (1 layer - 100 mic.) | 210.4%
| Lean concrete wire mesh installation (100 mm x 100 mm - 5 mm)(horizontal) |  | m² | 0.3 | 0.20446 | 146.7% | Lean concrete wire mesh installation (100 mm x 100 mm - 5 mm)(horizontal) | 146.7%
| Lean concrete Pouring (B15 - h= 10 cm)(horizontal) |  | m³ | 1.75 | 3.1158 | 56.17% | Lean concrete Pouring (B15 - h= 10 cm)(horizontal) | 56.17%
| Lean concrete wire mesh installation (100 mm x 100 mm - 5 mm)(vertical) |  | m² | 0.35 | 0.59167 | 59.15% | Lean concrete wire mesh installation (100 mm x 100 mm - 5 mm)(vertical) | 59.15%
| Vertical lean concrete formwork |  | m² | 1.8 | 3.1278 | 57.55% | Vertical lean concrete formwork | 57.55%
| Lean concrete Pouring (B15 - t=15 cm)(vertical) |  | m³ | 1.5 | 4.496 | 33.36% | Lean concrete Pouring (B15 - t=15 cm)(vertical) | 33.36%
| Horizontal water insulation (2 layers - Tehnoelast EPP w/ primer - 4mm) |  | m² | 1.5 | 0.2856 | 525.2% | Horizontal water insulation (2 layers - Tehnoelast EPP w/ primer - 4mm) | 525.2%
| Vertical water insulation (2 layers - Tehnoelast EPP w/ primer - 4mm) |  | m² | 2 | 0.94344 | 212% | Vertical water insulation (2 layers - Tehnoelast EPP w/ primer - 4mm) | 212%
| Water insulation around existing steel columns |  | pcs | 25 | 6.9891 | 357.7% | Water insulation around existing steel columns | 357.7%
| Protective screed above water insulation (h= 5 cm) |  | m³ | 1.5 | 4.7422 | 31.63% | Protective screed above water insulation (h= 5 cm) | 31.63%
C12 | Foundation R/C Works | [5 empty] | Foundation Formwork | 82.96%
| Foundation Formwork |  | m² | 1.8 | 2.1698 | 82.96% | Foundation Reinforcement | 110.4%
| Foundation Reinforcement |  | ton | 35 | 31.7003 | 110.4% | Foundation Reinforced Concrete | 246%
| Foundation Reinforced Concrete |  | m³ | 1.4 | 0.56915 | 246% | R/C Slab Demolishing Works (-5 Floor) (inc. Cleaning) | 13.35%
C19 | R/C Demolishing Works | [5 empty] | Substructure R/C Columns Formwork | 26.99%
| R/C Slab Demolishing Works (-5 Floor) (inc. Cleaning) |  | m² | 5 | 37.4483 | 13.35% | Substructure R/C Columns Reinforcement | 49.03%
| Substructure R/C Works | [5 empty] | Substructure R/C Columns Concrete | 47.79%
| R/C Structural Columns (B50 - 407 kg/m³) | [5 empty] | Substructure R/C Shear-Walls Formwork | 34.87%
| Substructure R/C Columns Formwork |  | m² | 1.8 | 6.6701 | 26.99% | Substructure R/C Shear-Walls Reinforcement | 47.82%
| Substructure R/C Columns Reinforcement |  | ton | 35 | 71.3837 | 49.03% | Substructure R/C Shear-Walls Concrete | 87.17%
| Substructure R/C Columns Concrete |  | m³ | 1.5 | 3.1384 | 47.79% | Substructure R/C Slabs Formwork | 157%
| R/C Structural Shear Walls (B50 - 270 kg/m³) | [5 empty] | Substructure R/C Slabs Reinforcement | 174.5%
| Substructure R/C Shear-Walls Formwork |  | m² | 1.8 | 5.162 | 34.87% | Substructure R/C Slabs Concrete | 116.6%
| Substructure R/C Shear-Walls Reinforcement |  | ton | 35 | 73.1982 | 47.82%
| Substructure R/C Shear-Walls Concrete |  | m³ | 1.5 | 1.7208 | 87.17%
R/C Structural Slabs (B35 - 332 kg/m³)
| Substructure R/C Slabs Formwork |  | m² | 1.8 | 1.1464 | 157%
| Substructure R/C Slabs Reinforcement |  | ton | 35 | 20.0629 | 174.5%
| Substructure R/C Slabs Concrete |  | m³ | 1.5 | 1.2861 | 116.6%
| Project Summary Activities | Cumulative Progress
| Mob. & Demob. & Health & Safety inc. Site Cleaning & Snow Removal | Planned | 60.73%
|  | Realized | 60.73%
| Civil Works | Planned | 19.72%
|  | Realized | 17.07%
| Architectural Works | Planned | 0%
|  | Realized | 0%
| Facade & Roofing Works | Planned | 0%
|  | Realized | 0%
| External Works | Planned | 0%
|  | Realized | 0%
| Mechanical Works | Planned | 0%
|  | Realized | 0%
| Electrical Works | Planned | 0%
|  | Realized | 0%
Project Materials Delivered to the Construction Site on April,15, 2008
| MATERIAL DESCRIPTION | Quantity | UNIT | Supplier
| Concrete B50 P4 F300 W12 | 18.5 | m3 | BETONSPECSTROY
| Rebar Ѳ36 | 16.03 | ton | DIPOS
| Rebar Ѳ8 | 5.13 | ton | DIPOS
| Concrete Milk | 1 | m3 | BETONSPECSTROY
| Timber 10x10 L=6 mt | 12 | m3 | STROYSERVIS
| PLYWOOD (Film-faced) 21x1220x2440 | 2.375 | m3 | PROMSTROYKONTRAKT
| Timber 10x10 L=6 mt | 40.62 | m3 | STROYSERVIS
| Rebar Ѳ28 | 37.24 | ton | BRAVIS
| Timber 10x10 L=6 mt | 12 | m3 | STROYSERVIS
| Concrete B50 P4 F300 W12 | 31 | m3 | BETONSPECSTROY
| Concrete B50 P4 F300 W12 | 43.5 | m3 | BETONSPECSTROY
| PLYWOOD (Film-faced) 12x1220x2440 | 10.002 | m3 | PROMSTROYKONTRAKT
| Concrete B50 P4 F300 W12 | 22 | m3 | BETONSPECSTROY
| Concrete B35 P4 F300 W10 | 353 | m3 | BETONSPECSTROY
| Concrete B35 P4 F300 W10 | 723 | m3 | BETONSPECSTROY
| Rebar Q32 | 86.5 | ton | EVROMETAL-STOLISA
| Rebar Q28 | 124.57 | ton | EVROMETAL-STOLISA

## Building Elevation
Donstroy-II Project Elevation and R/C Works Progress
| .+146,00 | [11 empty] | .+146,00
[6 empty] | Net Slab Area = 484 m² | [8 empty] | SUPERSTRUCTURE
.+34 Floor | .+142,80 | [11 empty] | .+142,80 | .+34 Floor
Net Slab Area = 484 m²
.+33 Floor | .+139,40 | [11 empty] | .+139,40 | .+33 Floor
Net Slab Area = 484 m²
.+32 Floor | .+136,00 | [11 empty] | .+136,00 | .+32 Floor
Net Slab Area = 1.005 m²
.+31 Floor | .+131,20 | [11 empty] | .+131,20 | .+31 Floor
Net Slab Area = 1.005 m²
.+30 Floor | .+126,40 | [11 empty] | .+126,40 | .+30 Floor
Net Slab Area = 1.373 m²
.+29 Floor | .+121,60 | [11 empty] | .+121,60 | .+29 Floor
Net Slab Area = 1.373 m²
.+28 Floor | .+116,80 | [11 empty] | .+116,80 | .+28 Floor
Net Slab Area = 1.373 m²
.+27 Floor | .+112,00 | [11 empty] | .+112,00 | .+27 Floor
Net Slab Area = 1.373 m²
.+26 Floor | .+107,20 | [11 empty] | .+107,20 | .+26 Floor
Net Slab Area = 1.373 m²
.+25 Floor | .+102,40 | [11 empty] | .+102,40 | .+25 Floor
Net Slab Area = 1.704 m²
.+24 Floor | .+98,20 | [11 empty] | .+98,20 | .+24 Floor
Net Slab Area = 1.704 m²
.+23 Floor | .+94,00 | [11 empty] | .+94,00 | .+23 Floor
Net Slab Area = 1.704 m²
.+22 Floor | .+89,80 | [11 empty] | .+89,80 | .+22 Floor
Net Slab Area = 2.070 m²
.+21 Floor | .+85,60 | [11 empty] | .+85,60 | .+21 Floor
Net Slab Area = 2.070 m²
.+20 Floor | .+81,40 | [11 empty] | .+81,40 | .+20 Floor
Net Slab Area = 2.070 m²
.+19 Floor | .+77,20 | [11 empty] | .+77,20 | .+19 Floor
Net Slab Area = 2.070 m²
.+18 Floor | .+73,00 | [11 empty] | .+73,00 | .+18 Floor
[7 empty] | Net Slab Area = 3.424 m² | [5 empty] | ,
.+17 Floor | .+68,00 | [11 empty] | .+68,00 | .+17 Floor
Net Slab Area = 5.014 m²
.+16 Floor | .+63,80 | [11 empty] | .+63,80 | .+16 Floor
Net Slab Area = 5.014 m²
.+15 Floor | .+59,60 | [11 empty] | .+59,60 | .+15 Floor
Net Slab Area = 5.014 m²
.+14 Floor | .+55,40 | [11 empty] | .+55,40 | .+14 Floor
Net Slab Area = 5.014 m²
.+13 Floor | .+51,20 | [11 empty] | .+51,20 | .+13 Floor
Net Slab Area = 5.126 m²
.+12 Floor | .+47,00 | [11 empty] | .+47,00 | .+12 Floor
Net Slab Area = 5.715 m²
.+11 Floor | .+42,80 | [11 empty] | .+42,80 | .+11 Floor
Net Slab Area = 5.928 m²
.+10 Floor | .+38,60 | [11 empty] | .+38,60 | .+10 Floor
Net Slab Area = 5.928 m²
.+9 Floor | .+34,40 | [11 empty] | .+34,40 | .+9 Floor
Net Slab Area = 5.928 m²
.+8 Floor | .+30,20 | [11 empty] | .+30,20 | .+8 Floor
Net Slab Area = 5.928 m²
.+7 Floor | .+26,00 | [11 empty] | .+26,00 | .+7 Floor
Net Slab Area = 6.633 m²
.+6 Floor | .+21,80 | [11 empty] | .+21,80 | .+6 Floor
Net Slab Area = 6.633 m²
.+5 Floor | .+17,60 | [11 empty] | .+17,60 | .+5 Floor
Net Slab Area = 8.337 m²
.+4 Floor | .+12,60 | [11 empty] | .+12,60 | .+4 Floor
Net Slab Area = 9.418 m²
.+3 Floor | .+8,40 | [11 empty] | .+8,40 | .+3 Floor
Net Slab Area = 9.040 m²
.+2 Floor | .+4,20 | [11 empty] | .+4,20 | .+2 Floor
Net Slab Area = 9.035 m²
.+1 Floor | .+0,00 | [11 empty] | .+0,00 | .+1 Floor
[5 empty] | Net Slab Area = 4.900 m² |  |  |  | Net Slab Area = 5.970 m² | Finish = 14/07/2008 |  |  |  |  | SUBSTRUCTURE
.-1 Floor | .-4,80 | Start = 20/05/2008 | [10 empty] | .-4,80 | .-1 Floor
[5 empty] | Net Slab Area = 2.300 m² |  |  |  | Net Slab Area = 2.900 m² | Finish = 25/06/2008
.-2 Floor | .-7,95 | Start = 12/05/2008 | [10 empty] | .-7,95 | .-2 Floor
[5 empty] | Net Slab Area = 2.300 m² |  |  |  | Net Slab Area = 2.900 m² | Finish = 05/06/2008
.-3 Floor | .-10,95 | Start = 30/04/2008 | [10 empty] | .-10,95 | .-3 Floor
[5 empty] | Net Slab Area = 2.300 m² |  |  |  | Net Slab Area = 2.900 m² | Finish = 22/05/2008
.-4 Floor | .-13,95 | Start = 15/04/2008 | [10 empty] | .-13,95 | .-4 Floor
|  |  | 4% |  | Net Slab Area = 2.300 m² |  |  |  | Net Slab Area = 2.900 m² | Finish = 10/05/2008
.-5 Floor | .-16,95 | Start = 10/04/2008 | [10 empty] | .-16,95 | .-5 Floor
[5 empty] | Net Slab Area = 2.300 m² |  |  |  | Net Slab Area = 2.900 m² | Finish = 24/04/2008
.-6 Floor | .-19,95 | Start = 25/02/2008 | [6 empty] | 77% |  |  |  | .-19,95 | .-6 Floor
100%
Raft Foundation |  | Start = 11/01/2008 | [8 empty] | Finish = 29/03/2008 |  |  | Raft Foundation
|  | WEST PART (SOUTH VIEW) | [5 empty] | EAST PART (SOUTH VIEW)
Note : The Customer submitted (-6 ; -5) Basement Floor Column Structural Working Drawings on February,21 , 2008 and Shear-Wall, Ramp and Slab Structural Working Drawings on March ,13-14 , 2008.
After obtaining necesary design documentation, ENKA commenced (-6 ; -5) R/C Column Works on February,25 , 2008 and (-6 ; -5) R/C Shear-Wall Works on March,15 , 2008 . ENKA commenced (-5) R/ C Slab
Scaffolding works on March, 28, 2008. Enka cast first slab concrete on April,05 .